## May-25
MATERIAL PROCURMENT & PAYMENT STATUS
SNO | ORDER DATE | DESCRIPCTION | SUPPLIER NAME | BILL DATE | DELIVERY DATE | FOR PROJECT | INVOICE NUMBER | AMOUNT | ORDERED PLACED BY | PAYMENT STATUS | PAYMENT DATE

## June-25
MATERIAL PROCURMENT & PAYMENT STATUS
SNO | ORDER DATE | DESCRIPCTION | SUPPLIER NAME | BILL DATE | DELIVERY DATE | FOR PROJECT | INVOICE NUMBER | AMOUNT | ORDERED PLACED BY | PAYMENT STATUS | PAYMENT DATE
1 | 2025-05-27 | Ready mix M25 for first floor Roof slab 49m3 @ 5500 rs | AK-Ready mix | 2025-05-29 | 2025-05-29 | P-01 |  | 269500 | Domnic | Completed | 2025-06-28 | CASH
2 | 2025-05-24 | Ramco cement 50 nos | Sriram Hardwares | 2025-05-26 |  | P-02 | SHR/1109 | 18250 | Yuviraj | Completed | 2025-06-02 | ACCOUNT
3 |  | Ramash Masthri | Labor contract |  |  | P-01 |  | 300000 | Vinoth | Completed | 2025-06-02 | CASH
4 | 2025-03-05 | Anna nagar MEP Drawings | MYDEEN muscat |  |  | P-01 |  | 10000 | Vinoth | Completed | 2025-06-05 | ACCOUNT
5 | 2025-05-30 | anna nagar 2.5 units Msand (263) | Pandian |  | 2025-05-31 | P-01 |  | 16560 | Yuviraj | Completed | 2025-06-10 | GPAY SABRISH
6 | 2025-06-07 | anna nagar 2.5 units Msand (275) | Pandian |  | 2025-06-08 | P-02 |  | 17380 | Yuviraj | Completed | 2025-06-10 | GPAY SABRISH
7 | 2025-05-30 | SNL Bricks | Rajesh |  | 2025-06-01 | P-02 |  | 31500 | Yuviraj | Completed | 2025-06-03 | CASH
8 | 2025-06-04 | SNL Bricks | Rajesh |  | 2025-06-05 | P-02 |  | 31500 | Yuviraj | Completed | 2025-06-13 | CASH
9 | 2025-06-09 | Steel For Foundation | Annai Axulirium | 2025-06-10 | 2025-06-10 | P-03 | 837/25-26 | 250445 | Vinoth | Completed | 2025-06-30 | CASH
10 |  | Ramash Masthri | Labor contract |  |  | P-01 |  | 300000 | Vinoth | Completed | 2025-06-11 | CASH
11 |  | Azhumalai Masthri | Labor contract |  |  | P-03 |  | 75000 | Vinoth | Completed | 2025-06-11 | CASH
12 | 2025-06-09 | SNL Bricks | Rajesh |  | 2025-06-05 | P-01 |  | 31500 | Yuviraj | Completed | 2025-06-13 | CASH
13 | 2025-06-12 | 100 Bags Cement -Ramco Create | V.S Enterpraise | 2025-06-13 | 2025-06-12 | P-03 | 131 | 37000 | Yuviraj | Completed | 2025-06-14 | ACCOUNT
14 | 2025-06-12 | M.Sand 682 cft @ 56.5 | T.K.G TRADERS | 2025-06-13 | 2025-06-12 | P-03 |  | 38533 | Yuviraj | Completed | 2025-06-18 | CASH
15 | 2025-06-12 | 20MM Aggre 682 cft @ 46.5 | T.K.G TRADERS | 2025-06-13 | 2025-06-12 | P-03 |  | 31713 | Yuviraj | Completed | 2025-06-18 | CASH
16 | 2025-06-13 | Electrical / DB Material | Golden Traders |  | 2025-06-14 | P-02 | 522 | 32500 | Yuviraj | Completed | 2025-06-14 | ACCOUNT
17 | 2025-06-13 | Door Frames | Bhuvaneswari timber |  | 2025-06-16 | P-02 |  | 36500 | Vinoth | Completed | 2025-06-16 | CASH
18 | 2025-06-13 | Flood light & Wire |  |  |  | P-03 |  | 3210 | Yuviraj | Completed | 2025-06-13
19 | 2025-06-07 | helmets site-Labours | Mactech pvt ltd |  |  | Office | 3790 | 3811 | Vinoth | Completed | 2025-06-11
20 | 2025-06-16 | SNL Bricks | Rajesh |  |  | P-01 |  | 63000 | Yuviraj | Completed | 2025-06-13 | CASH
21 | 2025-06-16 | 100 Bags Cement -Ramco Create | Sriram Hardwares |  |  | P-03 | SHR/1540 | 37000 | Yuviraj | Completed | 2025-06-23 | ACCOUNT
22 | 2025-06-16 | bizet subscription | alice mary |  |  | Office |  | 10750 | Vinoth | Completed | 2025-06-16 | ACCOUNT
23 | 2025-06-17 | bizet Broucher | alice mary |  |  | Office |  | 1500 | Vinoth | Completed | 2025-06-17 | ACCOUNT
24 | 2025-06-17 | bizet subscription | alice mary |  |  | Office |  | 2400 | Vinoth | Completed | 2025-06-17 | ACCOUNT
25 |  | Pusparaj- | Electrical Labor |  |  | P-02 |  | 35000 | Domnic | Completed | 2025-06-17 | CASH | domnic
26 |  | 100 Bags Cement -Ramco Create | Sriram Hardwares |  |  | P-03 | SHR/1671 | 35000 | Yuviraj | Completed | 2025-06-23 | ACCOUNT
27 |  | 50 Bags Cement -Ramco | Sriram Hardwares |  |  | P-01 | SHR/1696 | 17500 | Yuviraj | Completed | 2025-06-23 | ACCOUNT
28 | 2025-06-22 | Plinth Beam Steel | Irfana steels |  | 2025-06-23 | P-03 | IR/660 | 90446 | Vinoth | Completed | 2025-06-23 | ACCOUNT
29 | 2025-06-26 | flyash brich 3000 @ 8 rs | A1 fly ash |  |  | P-03 |  | 24000 | Vinoth | Completed | 2025-06-27 | CASH
30 | 2025-06-27 | flyash brich 3500 @ 8rs | A1 fly ash |  |  | P-03 |  | 28000 | Vinoth | Completed | 2025-06-27 | CASH
31 | 2025-06-16 | M.Sand 682 cft @ 56.5 | T.K.G TRADERS |  |  | P-03 |  | 38533 | Yuviraj | Completed | 2025-06-27 | CASH
32 | 2025-06-26 | 20MM Aggre 682 cft @ 46.5 | T.K.G TRADERS |  |  | P-03 |  | 31713 | Yuviraj | Completed | 2025-06-27 | CASH
33 | 2025-06-25 | 5 nos 3.5 feet 2nd teaks | Bhuvaneswari timber |  |  | P-02 |  | 3000 | Vinoth | Completed | 2025-06-25 | ACCOUNT
34 |  | Azhumalai -Stage 2 payment | Labor contract |  |  | P-03 |  | 120000 | Vinoth | Completed | 2025-06-28 | CASH
|  | Arun structural -consult | consultant fee |  |  | P-01 |  | 10000 | Vinoth | Completed | 2025-06-27 | ACCOUNT
|  | Pusparaj- | Electrical Labor |  |  | P-01 |  | 15000 | Vinoth | Completed | 2025-06-06 | ACCOUNT
|  | Baradhan -For Elevation | Architect |  |  | P-01 |  | 5000 | Vinoth | Completed | 2025-06-27
TOTAL | [7 empty] | 2102744
Formulas:
PAYMENT DATE = [BILL DATE]+30

## JULY-25
MATERIAL PROCURMENT & PAYMENT STATUS
SNO | ORDER DATE | DESCRIPCTION | SUPPLIER NAME | BILL DATE | DELIVERY DATE | FOR PROJECT | INVOICE NUMBER | AMOUNT | ORDERED PLACED BY | PAYMENT STATUS | PAYMENT DATE
1 | 2025-06-07 | helmets site- Engineers white | amazon - card |  |  | Office |  | 1039 | Vinoth | Completed | 2025-07-19
2 | 2025-06-09 | helmets site - Client grey | amazon - card |  |  | Office |  | 1980 | Vinoth | Completed | 2025-07-19
3 | 2025-06-26 | M.Sand 682 cft @ 56.5 | T.K.G TRADERS |  |  | P-03 |  | 38533 | Yuviraj | Completed | 2025-07-15 | CASH
4 | 2025-06-25 | SNL Bricks -3000 nos | Rajesh |  | 2025-06-26 | P-01 |  | 31500 | Yuviraj | Completed | 2023-07-07 | CASH
5 | 2025-06-28 | SNL Bricks -3000 nos | Rajesh |  | 2025-06-30 | P-01 |  | 31500 | Yuviraj | Completed | 2023-07-07 | CASH
6 | 2025-07-01 | SNL Bricks -3000 nos | Rajesh |  | 2025-07-01 | P-01 |  | 31500 | Yuviraj | Completed | 2023-07-07 | CASH
7 | 2025-07-02 | SNL Bricks -3000 nos | Rajesh |  | 2025-07-02 | P-01 |  | 31500 | Yuviraj | Completed | 2023-07-07 | CASH
8 |  | 2 units 20 Aggrigate (200) | Pandian |  | 2025-06-17 | P-03 |  | 10600 | Yuviraj | Completed | 2025-07-16 | CASH
9 |  | 2.5 units Msand (263) | Pandian |  | 2025-06-20 | P-01 |  | 16400 | Yuviraj | Completed | 2025-07-16 | CASH
10 |  | 2.5 units Msand (263) | Pandian |  | 2025-06-29 | P-01 |  | 16200 | Yuviraj | Completed | 2025-07-16 | CASH
11 | 2025-06-30 | 10.780 I STEEL | Sriram Hardwares |  | 2025-06-30 | P-01 | SRH/1880 | 684790 | Vinoth | Completed | 2023-07-15 | CASH/credit card
12 | 2025-06-30 | 10.780 I STEEL DELIVERY CHARGES | Sriram Hardwares |  | 2025-06-30 | P-01 |  | 15000 | Vinoth | Completed | 2023-07-15 | PETTY CASH YUVIRAJ
13 | 2025-07-02 | BRUSH BOND | TRADE WINGS |  | 2025-07-02 | P-01 | 4741 | 2444 | Yuviraj | Completed | 2025-07-02
14 | 2025-07-03 | SNL Bricks -3000 nos | Rajesh |  | 2025-07-03 | P-01 |  | 31500 | Yuviraj | Completed | 2023-07-07
15 | 2025-05-16 | Msand 389.28 cft @60 rs | Chennai Civil supply | 0733 | 2025-05-16 | P-02 |  | 23356.8 | Yuviraj | Completed | 2025-07-16 | CASH
16 | 2025-06-04 | Aggregate 336 @54 | Chennai Civil supply | 0961 | 2025-06-04 | P-02 |  | 18154.26 | Yuviraj | Completed | 2025-07-16 | CASH
17 | 2025-05-31 | Aggregate 336 @54 | Chennai Civil supply | 1036 | 2025-05-31 | P-01 |  | 18154.26 | Yuviraj | Completed | 2025-07-16 | CASH
18 |  | 50 bags cement | Sriram Hardwares |  | 2025-07-04 | P-01 | SRH/1943 | 17750 | Yuviraj | Completed | 2023-07-15 | account
20 |  | 20MM Aggre 674 cft @ 46.5 | T.K.G TRADERS |  | 2025-07-08 | P-03 |  | 31341 | Yuviraj | Completed | 2025-07-15 | CASH
21 | 2025-07-04 | 100 Bags Cement -Ramco Create | V.S Enterpraise |  | 2025-07-11 | P-02 | 185 | 33500 | Yuviraj | Completed | 2025-07-19 | account
22 | 2025-07-03 | Bitufix & brush bond | Aqua protection |  |  | P-03 | 05-2025-26 | 9591 | Yuviraj | Completed | 2025-07-03 | CASH
23 | 2025-07-08 | SNL Bricks -3000 nos | Rajesh |  | 2025-07-09 | P-01 |  | 31500 | Yuviraj | Completed | 2025-07-16 | CASH
24 |  | Pusparaj- | Electrical Labor |  |  | P-02 |  | 25000 | Domnic | Completed | 2023-07-08 | CASH
25 |  | JV Board Anna Nagar | Naza Engineering |  | 2025-06-05 | Office |  | 19000 | Domnic | Completed | 2025-07-17 | CASH
26 | 2025-07-09 | GF Metal Box | Golden Traders |  | 2025-07-09 | P-01 |  | 1292 | Yuviraj | Completed | 2025-07-09 | account | s
27 | 2025-07-09 | CPVC Pipes Toilet | Sri Balaji Agencies |  |  | P-02 |  | 27914 | Yuviraj | Completed | 2025-07-09 | CASH
28 | 2025-07-11 | second floor roof ele Material | Golden Traders | 686 |  |  |  | 6694 | Yuviraj | Completed | 2025-07-15 | account
29 | 2025-07-11 | Column Steel | Irfana steels |  | 2025-07-11 | P-03 | IR/787 | 86440 | Vinoth | Completed | 2025-07-11 | Credit card
30 | 2025-07-11 | Column Steel | Irfana steels |  | 2025-07-11 | P-03 | IR/788 | 17894 | Vinoth | Completed | 2025-07-11 | Credit card
31 | 2025-07-10 | SNL Bricks -3000 nos | Rajesh |  | 2025-07-11 | P-01 |  | 31500 | Yuviraj | Completed | 2025-07-16 | CASH
32 |  | P.sand 674 cft @ 66 | T.K.G TRADERS |  | 2025-07-12 | P-02 |  | 44484 | Yuviraj | Completed | 2025-07-15 | CASH
33 |  | azhumalai - Cement | Local supply |  |  | P-03 |  | 10000 | Yuviraj | Completed | 2025-07-09 | CASH
|  | car battery seltos |  |  |  | office |  | 7000 | Vinoth | Completed | 2025-07-15
|  | company account |  |  |  | office |  | 200000 | Vinoth | Completed | 2025-07-15 | to account
34 |  | Ramash Masthri | Labor contract |  |  | P-01 |  | 300000 | Vinoth | Completed | 2025-07-15 | CASH
35 |  | Ramash Masthri -sand material | [5 empty] | 21000 | Domnic | Completed | 2025-07-15 | CASH | domnic
36 |  | Domnic | Advance |  |  | office |  | 50000 |  | Completed | 2025-07-15 | CASH | vinoth
37 |  | VINOTH- VIDYA NATHAN SCHOOL FEE | Advance |  |  | office |  | 60000 |  | Completed | 2025-07-15 | CASH
38 |  | VINOTH for magesh | Advance |  |  | office |  | 28000 |  | Completed | 2025-07-15 | CASH
39 |  | 2 units Msand (270) | Pandian |  | 2025-07-04 | P-01 |  | 17000 | Yuviraj | Completed | 2025-07-16 | CASH
40 |  | Petty cash Yuviray |  |  |  | office |  | 20000 | Vinoth | Completed | 2025-07-15 | CASH
41 |  | Pusparaj- | Electrical Labor |  |  | P-01 |  | 25000 | Domnic | Completed | 2025-07-19 | CASH
42 |  | Pusparaj- | Electrical Labor |  |  | P-02 |  | 15000 | Domnic | Completed | 2025-07-19 | CASH
43 | 2025-07-21 | 9 units filling sand x 750 | Azhumalai |  | 2025-07-21 | P-03 |  | 117000 | Yuviraj | Completed | 2025-07-22 | CASH
44
45 | 2025-07-21 | 100 bags cement | V.S Enterpraise |  | 2025-07-21 | P-01 | 212 | 33500 | Yuviraj | Completed | 2025-07-28
46
48 |  | stage 3 payment -basement | Azhumalai |  |  | P-03 |  | 75000 | Domnic | Completed | 2025-07-26 | cash
49 |  | Watchman salary | Azhumalai |  |  | P-03 |  | 5000 | Domnic | Completed | 2025-07-26 | cash
50 |  | Pest control |  |  |  | P-03 |  | 4865 | Domnic | Completed | 2025-07-26 | cash
51 |  | Ramash Masthri | Labor contract |  |  | P-01 |  | 500000 | vinoth | Completed | 2025-07-30
52
53
54
55
56
57
58
TOTAL | [7 empty] | 2876416.32
Formulas:
PAYMENT DATE = [ORDER DATE]+7

## AUG-25
MATERIAL PROCURMENT & PAYMENT STATUS
SNO | ORDER DATE | DESCRIPCTION | SUPPLIER NAME | BILL DATE | DELIVERY DATE | FOR PROJECT | INVOICE NUMBER | AMOUNT | ORDERED PLACED BY | PAYMENT STATUS | PAYMENT DATE
|  | yuviraj petty cash | Petty cash |  |  |  |  | 10000 |  | Completed | 2025-08-02 | cash
|  | Vinoth salary | salary |  |  |  |  | 56000 |  | Completed | 2025-08-03 | cash
| 2025-07-17 | M.sand 4 units @63 | T.K.G TRADERS |  | 2025-07-17 | P-01 |  | 22230 | Yuviraj | Completed | 2025-08-04 | cash
| 2025-07-25 | Msand 6 units ordered | T.K.G TRADERS |  | 2025-07-27 | P-03 |  | 36905 | Yuviraj | Completed | 2025-08-04 | cash
| 2025-07-26 | P.sand 6 units ordered | T.K.G TRADERS |  | 2025-07-30 | P-02 |  | 43136 | Yuviraj | Completed | 2025-08-04 | cash
| 2025-07-25 | 100 bags cement | V.S Enterpraise |  | 2025-07-25 | P-03 | 219 | 33500 | Yuviraj | Completed | 2025-08-04 | account
| 2025-07-28 | 100 bags cement | V.S Enterpraise |  | 2025-07-29 | P-02 | 221 | 33500 | Yuviraj | Completed | 2025-08-05 | account
|  | SNL Bricks -3000 nos | Rajesh |  |  | P-01 |  | 32500 | Yuviraj | Completed | 2025-08-06 | cash
| 2025-07-25 | SNL Bricks -3000 nos | Rajesh |  | 2025-07-26 | P-01 |  | 32500 | Yuviraj | Completed | 2025-08-06 | cash
| 2025-07-28 | SNL Bricks -3000 nos | Rajesh |  | 2025-07-30 | P-03 |  | 34000 | Yuviraj | Completed | 2025-08-06 | cash
| 2025-08-03 | SNL Bricks -3000 nos | Rajesh |  | 2025-08-04 | P-01 |  | 33000 | Yuviraj | Completed | 2025-08-06 | cash
|  | sump payment | Azhumalai |  |  | P-03 |  | 65000 | Domnic | Completed | 2025-08-06 | cash
| 2025-07-22 | M.sand 275 units @ 63 rs | Pandian |  | 2025-07-22 | P-01 |  | 17325 | Yuviraj | Completed | 2025-08-07 | cash
| 2025-07-23 | 20mm aggrigate 2 units @52.5 | Pandian |  | 2025-07-23 | P-01 |  | 10500 | Yuviraj | Completed | 2025-08-07 | cash
| 2025-07-22 | SNL Bricks -3000 nos | Rajesh |  | 2025-07-22 | P-01 |  | 32500 | Yuviraj | Completed | 2025-08-06 | cash
| 2025-07-21 | 300cft filling @14 rs | Velavan Blue Metal |  | 2025-07-21 | P-03 |  | 4200 | Yuviraj | Completed | 2025-08-09 | cash
| 2025-07-23 | 40 mm aggrigate 275 @ 44 rs 2 unit | Velavan Blue Metal |  | 2025-07-23 | P-03 |  | 12100 | Yuviraj | Completed | 2025-08-09 | cash
|  | yuviraj petty cash | Petty cash |  |  |  |  | 10000 |  | Completed | 2025-08-09 | cash
|  | yuviraj petty cash | Petty cash |  |  |  |  | 20000 |  | Completed | 2025-08-14 | cash
| 2025-08-08 | SNL Bricks -3000 nos | Rajesh |  | 2025-08-08 | P-01 |  | 34000 | Yuviraj | Completed | 2025-08-16 | cash
| 2025-08-08 | SNL Bricks -3000 nos | Rajesh |  | 2025-08-09 | P-01 |  | 34000 | Yuviraj | Completed | 2025-08-16 | cash
| 2025-08-08 | SNL Bricks -3000 nos 2nd load | Rajesh |  | 2025-08-09 | P-01 |  | 34000 | Yuviraj | Completed | 2025-08-16 | cash
| 2025-08-11 | SNL Bricks -3000 nos | Rajesh |  | 2025-08-11 | P-01 |  | 35000 | Yuviraj | Completed | 2025-08-16 | cash
| 2025-08-11 | SNL Bricks -3000 nos | Rajesh |  | 2025-08-12 | P-01 |  | 35000 | Yuviraj | Completed | 2025-08-16 | cash
|  | Ganesn Pending rent | ganesan |  |  | office |  | 40000 | vinoth | Completed | 2025-08-16
|  | Ramash Masthri | Labor contract |  |  | P-01 |  | 300000 | Vinoth | Completed | 2025-08-20 | CASH to mari
|  | advance for shuttring material | Azhumalai |  |  | P-03 |  | 50000 | Domnic | Completed | 2025-08-20 | cash
|  | Pusparaj- | Electrical Labor |  |  | P-02 |  | 40500 | Vinoth | Completed | 2025-07-19 | CASH to prakesh
|  | advance for shuttring material | Azhumalai |  |  | P-03 |  | 50000 | Domnic | Completed | 2025-08-20 | cash
| 2025-07-14 | Ready mix 3 floor 49m3 2.646 lac | Amaze Ready mix |  |  | P-01 |  | 200000 | Domnic | Completed | 2025-08-30 | cash | partial payment
TOTAL | [7 empty] | 1391396
Formulas:
PAYMENT DATE = [DELIVERY DATE]+7

## SEPT-25
MATERIAL PROCURMENT & PAYMENT STATUS
SNO | ORDER DATE | DESCRIPCTION | SUPPLIER NAME | BILL DATE | DELIVERY DATE | FOR PROJECT | INVOICE NUMBER | AMOUNT | ORDERED PLACED BY | PAYMENT STATUS | PAYMENT DATE
|  | M.sand units @ 63 | Pandian |  |  | P-01 |  | 23300 | Yuviraj | Completed | 2025-09-02 | cash
|  | Sathyaraj Bricks | Ramesh |  |  | P-01 |  | 34000 | Yuviraj | Completed | 2025-09-02 | cash
|  | Vinoth Salary 33+30 |  |  |  | office |  | 66000 |  | Completed | 2025-09-02 | cash
|  | Ramash Masthri | Labor contract |  |  | P-01 |  | 500000 | Yuviraj | Completed | 2025-09-04 | cash @ palavaram site
TOTAL | [7 empty] | 623300