## P-01
SUMMARY- PAYMENT RECEIVED
PROJECT CODE # - |  | P01/24-06
PROJECT NAME: CONSTRUCTION OF G+3 VILLA PROJECT @ B-BLOCK ANNA NAGAR EAST
CLIENT : MR.ANANDARAMAN.K | [5 empty] | Total Received
SNO | DATE | DESCRIPTION | AMOUNT |  |  |  | Remarks
|  |  | BANKING | CASH | G.PAY |  | Inv-No | Date | Value | Comment
1 | 2024-07-31 | Soil Test Advance |  |  |  |  | client has asked no to consider in our payment, Let it be as he paid for the first work executed | 30000
2 | 2024-08-03 | Soil Test Part Payment | [5 empty] | 30000
3 | 2024-08-20 | Soil Test Final Payment | [5 empty] | 10000
1 | 2024-08-22 | Order Confirmation -Token Advance -Cheque | 100000 |  |  | 2000000
| 2024-08-22 | Advance paid to account transfer (test) | 1000
| 2024-08-22 | Advance paid to account transfer (test) | 2000
| 2024-09-25 | Contract signed and Advance paid as cash Office Egmore |  | 1000000
| 2024-09-25 | Advance paid to account transfer | 397000
| 2024-09-25 | Advance paid to account transfer | 500000
2 | 2024-09-25 | Advance paid to account transfer | 1000000 |  |  | 2800000 | 12/04&05
| 2024-11-06 | Payment Received @ Aynavaram Home |  | 1800000
3 | 2025-12-08 | Online Transfer to cubits account & at Office Egmore | 500000 | 1000000 |  | 2500000 | 12/06 | 2024-12-31
| 2025-01-14 | Power 4 Ever to cubits Accounts | 1000000 |  |  |  | 01/07 | 2025-01-23
4 | 2025-03-19 | Advance paid to account transfer | 500000 |  |  | 2100000 | 03/9 | 2025-03-12
| 2025-03-20 | Advance paid to account transfer | 500000 |  |  |  | 03/10 | 2025-03-17
| 2025-03-20 | Received At Site From Solomon |  | 500000
| 2025-04-01 | Cash Given to Vinoth at Egmore Office |  | 600000
5 | 2025-04-23 | Advance paid to account transfer | 500000 |  |  | 2000000 | Inv-04-01 | 2025-05-09 | 500752
| 2025-04-30 | Cash Given to Domnic Christofer |  | 1000000
| 2025-05-13 | Cash Given to Domnic Christofer @ Egmore Office |  | 500000 | [5 empty] | 1.5 lac excess payment made
6 | 2025-05-31 | Cash Received From Solomon from site |  | 700000 |  | 1700000
| 2025-06-01 | Advance paid to account transfer | 500000 |  |  |  | Inv-04-02
| 2025-06-02 | Advance paid to account transfer | 500000 |  |  |  |  | 2025-05-31 | 1000000
7 | 2025-07-14 | Cash Given to Vinoth at Site during concrete |  | 2000000 |  | 4000000
7a | 2025-08-06 | Cash Given to yuviraj at Site by soloman |  | 1000000
| 2025-08-30 | Cash Given to Vinoth at Site by Anandaraman |  | 1000000
8 | 2025-09-02 | Medtech to sixty cubits account | 500000 |  |  | 1499000
| 2025-09-02 | Sinewaves to Sixtycubits account | 3001
| 2025-09-03 | Sinewaves to Sixtycubits account | 496999
| 2025-09-03 | Sinewaves to Sixtycubits account | 499000
9 | 2025-11-01 | Cash Given to Vinoth at site |  | 2000000 |  | 2000000
10 | 2025-11-17 | Cash Given to Yuviraj at site |  | 1500000 |  | 1500000
11 | 2025-12-03 | Account Transfer From Personal Account to Sixtycubits | 1000000 |  |  | 1000000
12 | 2026-01-07 | Cash Given to Vinoth at site |  | 2000000 |  | 2000000
13 | 2026-02-09 | Cash Given to Vinoth at ABM Madhavaram |  | 1500000 |  | 1500000
14 | 2026-02-14 | Cash Given to yuviraj At Home |  | 2500000 |  | 2500000
15 | 2026-02-23 | Gpay to painter -Salary (25+50) |  |  | 75000 | 75000
16 | 2026-02-26 | Gpay to Saravan Samuel (25+25) |  |  | 50000 | 50000
17 | 2026-03-01 | Gpay to Pushparaj |  |  | 33000 | 33000
18 | 2026-03-03 | Magesh kumar |  |  | 20000 | 20000
19 | 2026-03-04 | New Garuda (wires polycab) 2 bills |  | 500000 |  | 500000
20 | 2026-03-04 | Cash Given to Domnic At site |  | 3000000 |  | 3000000
21 | 2026-03-05 | Gpay to painter -Salary (30+15) |  |  | 45000 | 45000
22 | 2026-03-07 | New Garuda (wires polycab) |  | 95075 |  | 95075
23 | 2026-03-09 | Marble Payment Online To vendor A1-Marbles |  | 245998 |  | 245998
24 | 2026-04-19 | Gpay to painter -Salary |  |  | 50000 | 50000
25 | 2026-03-20 | Aquant Payment - 17-03 to 20-03-26 |  | 1252911 |  | 1252911
26 | 2026-03-21 | rahib khan Marble laying |  |  | 50000 | 50000
27 | 2026-03-21 | Gpay to Pushparaj |  |  | 35000 | 35000
28 | 2026-03-21 | Gpay to Tiles Layer baskar |  |  | 15000 | 15000
29 | 2026-03-26 | Account Transfer From Personal Account to Sixtycubits | 1000000 |  |  | 1000000
30 | 2026-03-31 | Maheshwaran - scaffolding |  |  | 50000 | 50000
31 | 2026-03-31 | Gpay to painter -Salary |  |  | 50000 | 50000
32 | 2026-04-07 | Johnsons Tile House |  |  | 21700 | 21700
33 | 2026-04-12 | Johnsons Tile House |  |  | 28550 | 28550
34 | 2026-04-13 | Tiles Layers- selvam iyappan |  |  | 20000 | 20000
35 | 2026-04-18 | Gpay to painter -Salary |  |  | 50000 | 50000
36 | 2026-04-18 | rahib khan Marble laying |  |  | 25000 | 25000
37 | 2026-04-19 | rahib khan Marble laying |  |  | 45000 | 45000
38 | 2026-04-29 | Sun Heart F1 and Common Bath Tiles Payment |  | 35920 |  | 35920
39 | 2026-05-02 | Gpay to Pushparaj |  |  | 30000 | 30000
40 | 2026-05-08 | Account Transfer From Personal Account to Sixtycubits | 500000 |  |  | 500000
41 | 2026-05-16 | Rajib Granite Payment |  |  | 40000 | 40000
42 | 2026-05-16 | Selvam Tiles Payment |  |  | 30000 | 30000
43 | 2026-05-18 | Balaraman ( varnish) |  |  | 10000 | 10000
44 | 2026-05-18 | Cash Given to Vinoth at site |  | 492500 |  | 492500
45 | 2026-05-20 | Cash Given to Vinoth at site |  | 500000 |  | 500000
46 | 2026-05-20 | Account Transfer From Personal Account to Sixtycubits | 500000 |  |  | 500000
47 | 2026-05-20 | Alex and arms Vetrififed tiles |  |  | 130000 | 130000
48 | 2026-05-21 | Alex and arms Vetrififed tiles |  |  | 23755 | 23755
49 | 2026-05-21 | A One marble- Kitchen counter top |  |  | 100038 | 100038
50 | 2026-05-22 | Kajaria white cool roof tile |  |  | 63674 | 63674
51 | 2026-05-23 | Gpay to Pushparaj 30+45+25 |  |  | 100000 | 100000
52 | 2026-05-24 | Selvam Tiles Payment |  |  | 20000 | 20000
53 | 2026-05-26 | Sumith Electrictions 25+45+29.5 |  |  | 99500 | 99500
54 | 2026-05-26 | Cash Given to Vinoth at site |  | 250000
55 | 2026-05-30 | Account Transfer From Personal Account to Sixtycubits | 250000 |  |  | 250000
56 | 2026-05-31 | Gpay to Pushparaj 40 |  |  | 40000 | 40000
57 | 2026-05-31 | Selvam Tiles Payment |  |  | 60000 | 60000
0
0
0
0
0
0
0
0
|  | Total Amount | 10749000 | 26972404 | 1410217 | 38881621
|  |  | Received | 39131621 |  |  |  | 11000 | 7.5 | 82500
|  |  | TDS Deducted | 1000 | [5 empty] | 14300
96800
|  |  | Total Received | 39132621

## P-02
SUMMARY- PAYMENT RECEIVED
PROJECT CODE # - |  | P02/24-06
PROJECT NAME: CONSTRUCTION OF G+2 VILLA PROJECT @ AVADI (SAMIRA LAYOUT)
CLIENT : MR.SABARISH SWAMINATHAN
SNO | DATE | DESCRIPTION | AMOUNT
1 | 2024-08-22 | Initial advacne on pooja date | 2500
2 | 2024-09-05 | Payment - for Elevation 3D | 5000
3 | 2024-10-08 | Payment - Made to piggot | 25000
4 | 2024-10-08 | Payment - Made to piggot | 25000
5 | 2024-12-28 | Payment - Made to Rajesh | 25000 | (cement )
6 | 2024-12-29 | Payment - Made to Rajesh | 22250
7 | 2024-12-30 | Payment - Made to Sivalingam | 25000
8 | 2025-01-03 | Payment - Made to Ramesh Masthri | 25000 | (Labor Payment)
9 | 2025-01-03 | Payment - Made to Ramesh Masthri | 25000 | (Labor Payment)
10 | 2025-01-04 | Payment - Made to Piggot | 25000
11 | 2025-01-08 | Payment - Made to Domnic | 25000 | salary
12 | 2025-01-11 | Payment - Made to Company Account | 50000
13 | 2025-01-11 | Payment - Made to Company Account | 25000
14 | 2025-01-11 | Payment - Made to Company Account | 100000
15 | 2025-02-13 | Payment - Made to Vinoth As cash | 100000
16 | 2025-02-14 | Payment - Made to Manai Sadayappan (sand fill) gpay | 27000
17 | 2025-02-15 | Payment - Made to Vinoth As cash -ramachandra (40+20+20) | 80000
18 | 2025-02-22 | Payment - Made to Vinoth As cash -in college | 50000
19 | 2025-03-03 | Payment - Made to Vinoth As cash -sangeeta restarunt(50+20) | 70000
20 | 2025-03-04 | Payment - Made to Nikitha Mithra for Bricks | 32500 | BRICK
21 | 2025-03-06 | Payment - Made to Mari Muthu Account payee | 25000
22 | 2025-03-08 | Payment - Made to Mari Muthu Account payee | 75000
23 | 2025-03-08 | Payment - Made to Mari Muthu Account payee | 100000
24 | 2025-03-08 | Payment - Made to Mari Muthu Account payee | 100000
25 | 2025-03-08 | Payment - Made to piggot GPAY | 25000 | Salary
26 | 2025-03-08 | Payment - Made to VINOTH GPAY | 25000
27 | 2025-03-12 | Payment - Made to SURYA PRAKESH | 32500 | BRICK
28 | 2025-03-15 | Payment - Made to VINOTH CASH (BP Pump) | 80000
29 | 2025-03-17 | Payment - Made to VINOTH GPAY | 25000 | Nig
30 | 2025-03-18 | Payment - Made to Mari Muthu Account payee | 100000
31 | 2025-03-18 | Payment - Made to Mari Muthu Account payee | 100000
32 | 2025-03-20 | Payment - Made to Suresh | 15000 | suresh filling annanagar
33 | 2025-03-20 | Payment - Made to Manai Sadayappan Gpay | 26000 | (sand fill)
34 | 2025-03-20 | Payment - Made to Yuvaraj Gpay | 10000 | (Petty cash )
35 | 2025-03-25 | Payment - Made to Joachim Gpay | 5000 | Hospital
36 | 2025-03-25 | Payment - Made to Pusparaj Electriction Gpay | 20000 | Advance
37 | 2025-03-26 | Payment - Made to VINOTH As Cash (Commerzone) | 180000
38 | 2025-03-26 | Payment - Made to Yuvaraj Gpay | 31500 | Brick Anna nagar
39 | 2025-03-27 | Payment - Made to Yuvaraj Gpay | 31500 | Brick avadi
40 | 2025-03-28 | Payment - Made to Sakthi Depot | 6000
41 | 2025-03-28 | Payment - Made to Elumalai JanaikiRaman | 12000
42 | 2025-04-02 | Payment - Made to piggot GPAY | 25000 | salary
43 | 2025-04-02 | Payment - Made to Rochelle Gpay | 50000 | salary
44 | 2025-04-05 | Payment - Made to Yuvaraj Gpay | 25000 | for anna nagar petty cash for fencing
45 | 2025-04-08 | Payment - Made to Mani R Gpay - for 10,190 bricks | 91710 | bricks for avadi
46 | 2025-04-08 | Payment - Made to Company Account | 250000
47 | 2025-04-15 | Payment - Made to Yuvaraj Gpay | 10000
48 | 2025-04-18 | Payment - Made to Company Account | 200000
49 | 2025-04-18 | Payment - Made to Company Account | 200000
50 | 2025-04-18 | Payment - Made to Company Account | 240000
51 | 2025-04-28 | Payment - Made to Yuvaraj Gpay | 10000 | petty cash
52 | 2025-05-07 | Payment - Made to Yuvaraj Gpay | 31500 | brick.anna nagar
53 | 2025-05-08 | Payment - Made to VINOTH GPAY | 25000 | C.card bill
54 | 2025-05-09 | Payment - Made to Surya Hardwares GPAY | 17500 | cement
55 | 2025-05-09 | Payment - Made to Sri ambigai Hardwares | 21719 | Isteel
56 | 2025-05-14 | Payment - Made to Lokesh & vinayagam | 91000 | brick avadi
57 | 2025-05-15 | Payment - Made to Pusparaj Electriction Gpay | 20000 | advance
58 | 2025-05-16 | Payment - Made to PJ Mani Gpay | 45580 | sand and aggregate
59 | 2025-05-21 | Payment - Made to VINOTH GPAY | 75000 | FOR sriram hardware steel payment
60 | 2025-05-22 | Payment - Made to Company Account | 400000 | FOR sriram hardware steel payment
61 | 2025-05-27 | Payment - Made to Surya Hardwares GPAY | 46000 | FOR sriram hardware steel payment & cement
62 | 2025-06-08 | Payment - Made to VINOTH GPAY | 30000
63 | 2025-06-10 | Payment - Made to Pandian Gpay | 33940 | for Msand Avadi and Annanagar
64 | 2025-06-13 | Payment - Made to vinoth CASH (DLF) | 400000
65 | 2025-07-08 | Payment - Made to vinoth CASH (DLF) | 350000
66 | 2025-08-02 | Payment - Made to Rochelle Gpay | 50000
67 | 2025-09-04 | Payment - Made to Rochelle Gpay | 50000
68 | 2025-09-09 | Payment - Made to vinoth near dlf | 500000
69 | 2025-09-19 | Payment - Made to vinoth near dlf | 500000
70 | 2025-09-19 | Bio septic tank | 19500
71 | 2025-09-20 | Bio septic tank | 19500
72 | 2025-10-01 | Upvc Payment Robert | 50000
73 | 2025-10-11 | Granite payment | 80374
74 | 2025-10-14 | Maindoor Advance | 20000
75 | 2025-10-18 | Ashok grill | 47500
76 | 2025-10-24 | haritha given cash to vinoth at site | 120000
77 | 2025-10-28 | g pay to yuviraj | 10000
78 | 2025-10-29 | advance payment to door | 40000
79 | 2025-10-29 | Aac block | 19800 | for anna nagar
80 | 2025-10-30 | Sabarish given cash to vinoth at site | 100000
81 | 2025-10-31 | Transfer to company account for sanitaryware-lakshmi ceramic | 120000
82 | 2025-11-06 | Paid for lock | 37000
83 | 2025-11-10 | sabarish paid to yuviraj for false celing wiring | 8300
84 | 2025-11-12 | lakshmi ceramics | 26965
85 | 2025-11-14 | Door Final Payment | 65000
86 | 2025-11-20 | to Domnic cash | 75000
87 | 2025-11-21 | to vinoth Cash | 95000
88 | 2025-11-26 | Paver block | 30000
89 | 2025-11-27 | to Domnic cash | 100000
90 | 2025-12-05 | Paver block final payment | 9000
91 | 2025-12-05 | shell door | 26000
92 | 2025-12-08 | Handrailing advance | 30000
93 | 2025-12-22 | Handrailing Balcony Glass | 38000
94 | 2026-02-05 | cnc works xavier | 51664
|  | Total Received | 6816302
|  | Bill Raised-013 | 6841484
|  | Received | -6816302
|  | Balance | 25182

## P-03
SUMMARY- PAYMENT RECEIVED
PROJECT CODE # - |  | P03/25-06
PROJECT NAME: CONSTRUCTION OF G+2 VILLA PROJECT @ PALAVARAM
CLIENT : MR.MURUGAN (MEGA SOLOR SOULTION) |  |  |  |  | Total Received
SNO | DATE | DESCRIPTION | AMOUNT |  |  | Remarks
|  |  | BANKING | CASH |  | Inv-No | Date | Value | Comment
1 | 2024-07-31 | Soil Test Advance |  |  |  | client has asked no to consider in our payment, Let it be as he paid for the first work executed | 30000
2 | 2024-08-03 | Soil Test Part Payment |  |  |  |  | 30000
3 | 2024-08-20 | Soil Test Final Payment |  |  |  |  | 10000
1 | 2025-05-23 | Order Confirmation -Token Advance |  | 319250 | 1960248
2 | 2025-06-09 | After mobilisation |  | 638470
3 | 2025-07-31 | basment | 7 |  |  | 25-26-07/03
4 | 2025-07-31 | basment | 199993
5 | 2025-08-01 | basment | 300320 |  |  |  | 2025-07-31 | 500320
6 | 2025-08-06 | 25-26-07/04 | 502208 |  |  | 25-26-07/04 | 2025-08-06 | 502208
7 | 2025-08-11 | Cash paid to Vinoth at site |  | 150000 | 470000
8 | 2025-09-29 | Cash paid to Vinoth at site |  | 320000
9 | 2025-10-15 | Inv 25-26/08 | 500320 |  | 875560 | 25-26-07/08 | 2025-10-13 | 502208
10 | 2025-12-17 | Inv 25-26/11 | 375240 |  |  | 25-26-07/11 | 2025-12-17 | 375240
11 | 2025-12-22 | Cash paid to domnic at site |  | 300000 | 999900
12 | 2025-12-30 | saravanan gpay |  | 49900
13 | 2025-12-30 | velevan gpay |  | 150000
14 | 2026-01-09 | Inv 25-26/01-12 | 500000
15 | 2026-02-04 | Cash at Tata showroom near site |  | 300000 | 950320
16 | 2026-03-01 | Paid to saravanan cash |  | 150000
17 | 2026-03-02 | Inv 25-26/03-13 | 500320
18 | 2026-03-16 | Paid to saravanan cheque |  | 100000 | 674075
19 | 2026-03-26 | Plumbing pipes Gpay |  | 21375
20 | 2026-03-30 | cash given to surya |  | 150000
21 | 2026-04-09 | From Murugan sir -Client Payment (yuviraj) |  | 40000
22 | 2026-04-30 | Gpay to Saravanan to Labors |  | 50000
23 |  | Inv 26-27/05-1 | 312700
|  | Total Amount | 3191108 | 2738995 | 5930103
|  |  | Total Received | 5930103

## P-04
SUMMARY- PAYMENT RECEIVED
PROJECT CODE # - |  | P04/25-10
PROJECT NAME: CONSTRUCTION OF Ground floor Flat @ Saligramam
CLIENT : MRS.G.SELVI |  |  |  |  | Total Received
SNO | DATE | DESCRIPTION | AMOUNT |  |  | Remarks
|  |  | BANKING | CASH |  | Inv-No | Date | Value | Comment
1 | 2024-07-31 | Soil Test Advance |  |  |  | client has asked no to consider in our payment, Let it be as he paid for the first work executed | 30000
2 | 2024-08-03 | Soil Test Part Payment |  |  |  |  | 30000
3 | 2024-08-20 | Soil Test Final Payment |  |  |  |  | 10000
1 | 2025-10-15 | Advance Payment Received at St.Mathias Church |  | 500000
2 | 2026-02-17 | Payment received at home car parking |  | 250000
3 | 2026-03-01 | Payment received at client Home |  | 250000
4 | 2026-04-15 | Payment received at client Home -by surya |  | 300000
5 | 2026-05-06 | Payment received at client Home -by surya |  | 200000
6
7
8
0
0
|  | Total Amount | 0 | 1500000 | 0
|  |  | Total Received | 1500000